## Workflow Map
Workflow ID | Workflow | Stakeholders | Handoff / Output | Information / Dependencies | Blocked by (workflow IDs) | Blocks # workflows | Notes / Risks
W1 | Customer onboarding & city profiling | Customer; Ops lead | Collect details and share with city coordinator | City, family size, budget, locality, move date, documents, facilities |  |  | Confirm all required customer fields are collected before handoff.
W2 | Budget & timeline | Customer; Ops lead | Match budget to market and reach out to partners | Target-city rent vs customer budget | W1 |  | Budget and target dates should be agreed before sourcing.
W3 | Property match & landlord sourcing | Property partners; City ops | Shortlist properties and share customer review sheet | Partner inventory availability | W1, W2 |  | Availability can change; record last-confirmed date.
W4 | Viewing (field & location) | Customer; Landlord/agent | Schedule viewing and capture feedback | Society rules and regulations | W3 |  | Track cancellations and customer feedback.
W5 | Agreement & policies | Legal/property vendor; Tenant | Prepare and sign documents | Stamp/bond paper; rent agreement | W3, W4 |  | Confirm terms, dates, names, and required documents.
W6 | Security & deposit | Customer; Finance team; Landlord | Record payment proof and coordinate key handover | Signed document; payment confirmation | W5 |  | Do not mark complete until payment is verified.
W7 | Pre-move inventory | Customer; Logistics ops | Provide item list/photos to mover sourcing | Photos/videos of items; full item count | W1 |  | Inventory changes can affect quote and vehicle size.
W8 | Mover sourcing & rate negotiation | Packers & movers; Logistics ops | Select vendor and confirm booking/contract | Destination; lift access; inventory | W1, W5, W7 |  | Review proposal: agreement/lease dates should be confirmed before final mover booking. Validate whether provisional bookings are allowed.
W9 | Moving rules & gate clearance | Driver; Guards; Customer; Society management | Approve loading/unloading and gate access | Move-out NOC and move-in NOC; gate pass | W1, W5, W8 |  | Review proposal: society may require the signed agreement before issuing move-in approval/NOC; confirm local society rules.
W10 | Essential utility setup | Utility suppliers; Ops | Submit applications and required documents | Electricity meter number and provider-specific documents | W5, W6 |  | Track application status and missing documents separately.
W11 | Internet & society access | Local vendors; Internet provider; Society | Schedule installation and confirm house readiness | Society-approved provider; access permissions | W5, W9 |  | Provider availability and installation slots may delay setup.
W12 | Paperwork & address changes | Customer; Paperwork worker | Pass customer documents to paperwork worker and track submissions | Bills, agreement, identity/address documents | W5, W6 |  | Requirements vary by institution; avoid storing unnecessary sensitive data.
W13 | Damage to goods / move-in inspection | Customer; Landlord; Ops; Mover | Record condition report and raise claims/disputes | Move-day inspection; photos; inventory | W6, W7, W8 |  | Review proposal: inspection/condition report often happens at key handover after deposit/payment; confirm QuickMove's actual handover sequence.
W14 | Local service providers | Local partners; Customer; City ops | Introduce vetted providers and collect feedback | Destination city/locality; customer preferences | W1 |  | Clarify vetting, availability, and any referral disclosure.
W15 | Partner billing | Finance ops; Vendor; Customer | Issue/reconcile final invoice and update rating | Completed move; extra charges; damage/breakage dispute status | W8, W13 |  | Resolve disputed charges before final settlement.

## Stakeholders
Group | Stakeholder | Role / involvement
Customer side | Customer | Provides requirements, documents, approvals, payments, feedback.
Customer side | Family members | May help define requirements and coordinate move-day decisions.
QuickMove | Ops lead | Owns intake, timeline, customer communication, and escalation.
QuickMove | City coordinator / city ops | Coordinates local property and service partners.
QuickMove | Logistics ops | Collects inventory, sources movers, and coordinates transport.
QuickMove | Finance team / finance ops | Verifies payments, reconciles invoices, and tracks disputes.
QuickMove | Paperwork worker | Tracks address changes and institution-specific submissions.
Property side | Property partners | Provide listings and coordinate availability.
Property side | Landlord / agent | Coordinates viewings, agreement, deposits, and property handover.
Property side | Legal/property vendor | Supports agreement preparation and policy checks.
Movers | Packers & movers | Quote, pack, transport, deliver, and report exceptions.
Movers | Driver | Coordinates access, arrival, loading, and unloading.
Society/building | Security guards | Check approvals and control loading/unloading access.
Society/building | Society management | Issues NOCs/gate passes and confirms move rules.
Utilities and services | Electricity / utility provider | Processes connection or account setup.
Utilities and services | Internet provider | Checks serviceability and schedules installation.
Utilities and services | Local service providers | Offer local services such as maid, cook, or clinic.

## Gaps to Add
Gap ID | Potential missing workflow | Why it matters | Decision (Add / Merge / Skip) | Likely owner(s) | When it happens
G1 | Old-home move-out coordination / NOC | Move-out access and society approval may be missed. | Add | Customer; old society; ops | Before move day
G2 | New-home move-in NOC / gate pass | Delivery can be blocked if new society approval is missing. | Add | Customer; new society; ops | Before move day
G3 | Move-in condition report | Pre-existing damage may be confused with moving damage. | Add | Customer; landlord; ops | At handover / move-in
G4 | Mover confirmation and reconfirmation | Vendor may cancel or fail to arrive, especially close to move date. | Add | Logistics ops; mover | 48 hours and 24 hours before move
G5 | Date change / rescheduling management | Lease start or customer move date may change and affect multiple workflows. | Add | Customer; ops; partners | Whenever date changes
G6 | Missing-document follow-up | Utility or paperwork requests may be blocked by unavailable documents. | Add | Customer; paperwork worker; utility provider | When a document is requested
G7 | Exception escalation / SLA tracking | Issues can sit in WhatsApp without a clear owner or deadline. | Add | Ops lead; workflow owner | When task is overdue or blocked
G8 | Customer completion confirmation and feedback | Move may be marked complete before customer confirms delivery and satisfaction. | Add | Customer; ops; mover | After delivery
G9 | Vendor quality / dispute resolution | Damage claims and extra charges may delay final billing and ratings. | Add | Finance ops; customer; mover | Before invoice closure

## Automation Ranking
Rank | Candidate workflow / automation | Reason for rank | Impact | Frequency | Failure cost | Evidence / assumptions to validate
1 | Relocation status tracker + overdue alerts | Best first layer because it gives the five-person ops team one shared view of owners, due dates, blockers, and next actions. Keep data entry low-effort with a city-specific checklist and dropdown statuses rather than asking staff to retype WhatsApp updates. | High | Likely high | High | Hypothesis: validate task-chasing time, overdue rate, and whether checklist fields can be captured once at onboarding.
2 | Agreement and document readiness tracker | W5 appears to block W6, W10, W11, and W12, so delays can affect deposits, utilities, internet setup, and address changes. This may deserve priority over mover sourcing if agreement/document delays are frequent or cause expensive downstream rescheduling. | High | Likely high | High | Validate agreement turnaround time, common missing documents, and how often a delay cascades into other workflows.
3 | Mover quote, booking, and reconfirmation checklist | Standardizing inventory, floor/lift access, parking, dates, quotes, and 48/24-hour confirmations can reduce quote disputes and day-of cancellations. Rank it below agreement readiness only if local data shows agreement delays are the larger bottleneck. | High | Likely high | High | Validate quote disputes, cancellations, manual comparison time, and cost of failed move-day bookings.
Important | This is a provisional ranking based on the workflow map, not measured operational data. Adjust the order after validating frequency, time saved, and failure cost with the ops team.

## Workflow Metrics
Workflow ID | Workflow | Suggested metric | How to measure | Target / baseline | Owner | Notes / edge cases
W1 | Customer onboarding & city profiling | Intake completeness rate; time to complete intake | Complete required fields ÷ total required fields; timestamp from signup to complete intake | Baseline first; then set target | Ops lead | Track missing move date, destination locality, access details, and documents.
W2 | Budget & timeline | Budget-fit rate; time to agree plan | Moves with agreed budget/timeline ÷ total moves; time from intake to approval | Baseline first; then set target | Ops lead | Flag unrealistic budgets and date changes.
W3 | Property match & landlord sourcing | Time to first shortlist; shortlist acceptance rate | Hours from requirements approval to shortlist; accepted listings ÷ listings shared | Baseline by city | City ops | Record listing freshness and unavailable properties.
W4 | Viewing (field & location) | Viewing completion rate; reschedule rate | Completed viewings ÷ scheduled viewings; rescheduled viewings ÷ scheduled viewings | Baseline first | City ops | Track customer, landlord, and agent cancellations separately.
W5 | Agreement & policies | Agreement turnaround time; first-pass document completeness | Time from selected property to signed agreement; complete submissions ÷ submissions | Baseline first; prioritize reducing avoidable delays | Property ops | Lease start date changes and missing identity/address documents can cascade downstream.
W6 | Security & deposit | Payment verification time; payment exception rate | Time from payment evidence to verified status; exceptions ÷ payments | Baseline first | Finance ops | Never treat a screenshot alone as verified payment if finance policy requires reconciliation.
W7 | Pre-move inventory | Inventory completeness; quote revision rate | Inventory records with required item/access details ÷ total; revised quotes ÷ quotes | Baseline first | Logistics ops | Large or fragile items, stairs, and late-added items can change quote.
W8 | Mover sourcing & rate negotiation | Time to confirmed quote; booking confirmation rate | Time from complete inventory to accepted quote; confirmed bookings ÷ requested bookings | Baseline by city/vendor | Logistics ops | Track provisional bookings, cancellations, and price changes.
W9 | Moving rules & gate clearance | Approval readiness by deadline; access failure rate | Moves with all approvals before cutoff ÷ moves; failed/blocked access events ÷ moves | Aim for approvals before move-day cutoff; validate cutoff per society | City ops | Old and new societies may have different NOC and gate-pass rules.
W10 | Essential utility setup | Utility activation on/before requested date; missing-document rate | Connections active by requested date ÷ requested connections; applications missing docs ÷ applications | Baseline by provider and city | Utility coordinator | Provider rules, meter number, and document requirements vary.
W11 | Internet & society access | Installation on-time rate; first-visit completion rate | Installations completed by scheduled date ÷ installations; completed on first visit ÷ visits | Baseline by provider and locality | Utility coordinator | Check serviceability, society-approved vendors, and installation slots.
W12 | Paperwork & address changes | Submission completion rate; average days to completion | Completed submissions ÷ requested updates; days from request to confirmation | Baseline by institution type | Paperwork worker | Each institution can require different documents and processing times.
W13 | Damage to goods / move-in inspection | Inspection completion rate; damage claim rate | Moves with timestamped condition report ÷ completed moves; claims ÷ moves | Condition report target: every move | Logistics ops | Capture photos, item, time, and acknowledgement; separate pre-existing damage.
W14 | Local service providers | Provider match time; customer satisfaction | Time from request to options; post-introduction rating or feedback response | Baseline first | City ops | Track provider availability, vetting status, and customer preferences.
W15 | Partner billing | Invoice closure time; disputed invoice rate | Days from move completion to closed invoice; disputed invoices ÷ invoices | Baseline first | Finance ops | Damage claims and extra charges can hold up settlement.